## Example
The Final year of the PhD Workshop - version May 2026
Instructions for trainers: Instructions for trainers: this is a Gantt chart template to help PhD candidates make a timeline for their final year. We encourage you to adapt this template to your institution before using it: maybe there is only one defence in your institution, or the timing between submission and defence is very different. Please review the text of each line (each task) to adapt to your university jargon and check that instructions for the semi-automatic deadline calculator stay correct (for example, the cell D58 might become D53 if you delete some lines!).
Instructions for PhD candidates: This is only an example that fits PhD candidates in the faculties of XX and YY. It is recommended that you fully adapt it to your needs, see the empty template on sheet 2 to create your own. Please also note that there is a semi-automatic deadline calculator below the chart.
PhD timeline - final year
| 2027 | [11 empty] | Remarks | color code:
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Institutional tasks, like teaching
End of my contract/scholarship | 2027 Nov: x November 30! |  | Experimental tasks
Teaching or assistantship duties ? | [13 empty] | Writing tasks | bar: 2027 Mar to 2027 Jun; 2027 Sep to 2027 Nov
Experiment X and Y | [13 empty] | Holidays | bar: 2027 Jan to 2027 Feb
Analyse data | [13 empty] | Administrative tasks | bar: 2027 Feb to 2027 Mar
Finish writing paper | [13 empty] | Preparing for jobs after the PhD | bar: 2027 Mar to 2027 Apr
Submit paper | 2027 May: x May 1 |  | x deadlines
Paper revisions | [12 empty] | Maybe you don't know when the journal will ask for revisions, but it is still good to include them in the timeline while being ready to adjust with reality | bar: 2027 Jul to 2027 Aug
Resubmit paper | 2027 Sep: x TBD
Holidays ?! | 2027 May: 1 week?; 2027 Aug: 2 weeks?; 2027 Nov: 1 week?; 2027 Dec: 2 weeks? | Don't forget to take some time off and to take care of yourself :)
Write Chapter 3 | bar: 2027 May
Write Introduction & Conclusion | bar: 2027 Jun
Ask supervisor for corrections | bar: 2027 Jul
Make corrections | bar: 2027 Jul
Prepare Defence | bar: 2027 Sep
Discuss jury composition with supervisor | bar: 2027 Jan
Send invitation to jury members | bar: 2027 Feb to 2027 Mar
Supervisor submit jury composition to doctoral school | 2027 Jun: x June 1
Ask doctoral school for ECTS certificate | 2027 Jun: x June 1
Submit thesis to jury and doctoral school | 2027 Aug: x August 1
Private defence | 2027 Sep: x September 15
Make corrections | bar: 2027 Sep
Public defence | 2027 Oct: x October 15
Print final thesis | bar: 2027 Oct to 2027 Dec
Submitting thesis to Library and order diploma | bar: 2027 Dec
Participate in Career development Workshops | 2027 Feb: x workshop ?; 2027 May: x workshop ?; 2027 Aug: x workshop ?
Write postdoc/funding application and/or update CV | bar: 2027 Mar to 2027 Jun
Apply for jobs or funding | 2027 Jun: x grant submission deadline ?
To help you calculate deadlines with retroplanning :
1. Enter the private defense date you are aiming for (in D58)
2. Adjust the number of days administratively required between the submission and the private defence (in C58)
=> it will calculate your submission deadline (in B58)
3. Adjust the minimum number of days administratively required between your private and your public defences (in E58)
=> it will calculate the earliest date possible for your public defence (in F58)
4. Adjust the maximum number of days administratively required between your private and your public defences (in E60)
=> it will calculate the latest date possible for your public defence (in F60)
5. Manually adjust your timeline above accordingly
Below is an example if you want to defend on September 15th, and the thesis has to be submitted minimum 35 days (5 weeks) before the private defense, and considering the minimum (21 days, 3 weeks) and maximum (84 days, 3 months) of days between the private and the public defences. Adapt this minimum and maximun of days according to the regulations in your doctoral program.
Do not modify formula in the cell below.
Enter the date or number you want in the cell below.
NB: To try to calculate other dates, look for the function "DATE".
Warning: it does not take into account weekends nor public holidays.
| Submission deadline | Minimum nb of days between submission and private defence | Private defence date | Minimum nb of days between private and public defences | Earliest public defence date possible
| 2027-08-11 | 35 | 2027-09-15 | 21 | 2027-10-06
|  |  |  | Maximum nb of days between private and public defences | Latest public defence date possible
|  |  |  | 84 | 2027-12-08

## Empty template
Final year of the PhD Workshop - version May 2026
Instructions: this is an empty template for you to create your own timeline, you can look at example in the other sheet. Please also note that there is a semi-automatic deadline calculator below the chart.
PhD timeline - final year
| 2027 | [11 empty] | Remarks
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Task 1
Task 2
To help you calculate deadlines with retroplanning :
1. Enter the private defense date you are aiming for (in D58)
2. Adjust the number of days administratively required between the submission and the private defence (in C58)
=> it will calculate your submission deadline (in B58)
3. Adjust the minimum number of days administratively required between your private and your public defences (in E58)
=> it will calculate the earliest date possible for your public defence (in F58)
4. Adjust the maximum number of days administratively required between your private and your public defences (in E60)
=> it will calculate the latest date possible for your public defence (in F60)
5. Manually adjust your timeline above accordingly
Below is an example if you want to defend on September 15th, and the thesis has to be submitted minimum 35 days (5 weeks) before the private defense, and considering the minimum (21 days, 3 weeks) and maximum (84 days, 3 months) of days between the private and the public defences. Adapt this minimum and maximun of days according to the regulations in your doctoral program.
Do not modify formula in the cell below.
Enter the date or number you want in the cell below.
NB: To try to calculate other dates, look for the function "DATE".
Warning: it does not take into account weekends nor public holidays.
| Submission deadline | Minimum nb of days between submission and private defence | Private defence date | Minimum nb of days between private and public defences | Earliest public defence date possible
| 2027-09-10 | 35 | 2027-10-15 | 21 | 2027-11-05
|  |  |  | Maximum nb of days between private and public defences | Latest public defence date possible
|  |  |  | 84 | 2028-01-07